## Sheet1
MINI PROJECT
Name | Abhilash
Project Start Date | Aug-23-2017
Project Estimated End Date | Sep-11-2017
Project End Date
Total Days
Working Hrs/day | 8
Leaves
DESIGN
Sl No | Task | Description | Estimated Start Date | Estimated End Date | Start Date | End Date | Estimated Hours | Time Taken(in Hr) | Done By | Status | Reviewed By | Lags
1 | Functional Document |  | 2017-08-20 | [5 empty] | Abhilash | Completed
2 | Database Design |  | 2017-08-21 | [5 empty] | Abhilash | Completed
3 | Database Design in SQL |  | 2017-08-23 | 2017-08-23 |  |  | 2 |  | Abhilash | Pending
4 | Stored Procedure | Will be doing side by side with coading | [6 empty] | Abhilash | Pending
5 | MasterPage Designing | Admin | 2017-08-23 | 2017-08-25 |  |  | 6 |  | Abhilash | Pending
6 | MasterPage Designing | User | 2017-08-23 | 2017-08-25 |  |  | 6 |  | Abhilash | Pending
CODING
Sl No | Task | Description | Estimated Start Date | Estimated End Date | Start Date | End Date | Estimated Hours | Time Taken(in Hr) | Done By | Status | Reviewed By | Lags
ADMIN MODULE
8 | Admin Login | Design | 2017-08-26
|  | Coding | 2017-08-26
|  | Unit Test | 2017-08-26
9 | Manage Category, Sub-category | Design | 2017-08-27
|  | Coding | 2017-08-27
|  | Unit Test | 2017-08-27
10 | Manage Product | Design | 2017-08-28
|  | Coding | 2017-08-28
|  | Unit Test | 2017-08-28
11 | Customer Feedback | Design | 2017-09-04
|  | Coding | 2017-09-04
|  | Unit Test | 2017-09-04
12 | Log Out | Design | 2017-09-05
|  | Coding | 2017-09-05
|  | Unit Test | 2017-09-05
13
PUBLIC USER MODULE
14 | Home Page | Design | 2017-08-29
|  | Coding | 2017-08-29
|  | Unit Test | 2017-08-29
15 | Display Items | Design | 2017-08-30
|  | Coding | 2017-08-30
|  | Unit Test | 2017-08-30
16 | User Registration | Design | 2017-08-31
|  | Coding | 2017-08-31
|  | Unit Test | 2017-08-31
17 | Purchase | Design | 2017-09-01
|  | Coding | 2017-09-01
|  | Unit Test | 2017-09-01
18 | Feedback | Design | 2017-09-02
|  | Coding | 2017-09-02
|  | Unit Test | 2017-09-02
19 | Favourites | Design | 2017-09-03
|  | Coding | 2017-09-03
|  | Unit Test | 2017-09-03
20 | Search Item | Design | 2017-09-04
|  | Coding | 2017-09-04
|  | Unit Test | 2017-09-04
21 | User Login and Log out | Design | 2017-09-06
|  | Coding | 2017-09-06
|  | Unit Test | 2017-09-06
22
23
Functionality Specific Document